## Issue Register
ID | Issue | Type | Status | Priority | Severity | Date Raised | Last Update | Decision Date | Closure Date | Raised by | Report Link | Decision | Description
1 | Budget was raised | Request for Change | Closed | High | Minor | 2022-11-04 | 2022-11-11 | 2022-11-11 | 2022-11-11 | Muskan Shah | Hyperlink to the repot, if any | The budget was raised from 5000 to 1000 | The cost of advertisments, rewards and risk management raised our costs
2 | Limited external help | Problem/Concern | Closed | Very High | Critical | 2022-10-15 | 2022-11-03 | 2022-11-03 | 2022-11-11 | Manahil Rana | None | Multiple programmers to help with the app | External help was needed from GDSC to provide help with the softwares
3 | No test run conducted | Off-Specification | Open | Medium | Minor | 2022-11-08 | 2022-11-08 |  |  | Nischal | None | Test run will be conducted in the future | Test run will give us the credibility of the app
4 | Photo Quality | Off-Specification | Open | Medium | Minor | 2022-11-08 | 2022-11-08 | 2022-11-09 | 2022-11-11 | Abdullah Rafique | None | Optical character recognition will be used | Photos can be blurry therefore the number plate might not be readable
5 | Number plate | Problem/Concern | Open | Medium | Major | 2022-11-10 | 2022-11-10 | 2022-11-11 | 2022-11-11 | Andrei Musca | None | The car owner will have to take the risk | If the number plate is not visible in the photo, there is no way that the owner can know for sure if its their car or not.
- - - - PRINCE2® Templates - - - -
A guide for this template, it’s latest version, and all other templates are available at mplaza.pm/templates
Also, you may be interested in using our PRINCE2 eLearning Courses available at mplaza.pm
Copyright 2018, Management Plaza
You can use this document for free in your projects and for your personal purposes. Redistributing this document or using it for training requires permission from Management Plaza.
This document is based on AXELOS PRINCE2® material. Reproduced under licence from AXELOS. All rights reserved.

## Definitions
Types of issue | Types of Status | Types of Priority | Types of Severity
Request for Change | Open | Very High | Critical
Off-Specification | Closed | High | Major
Problem/Concern |  | Medium | Minor
Low
Very Low