## Issue Register
ID | Title | Type | Status | Date Raised | Last Update | Closure Date | Raised by | Owner | Actionee | Cause | Event | Effect | Probability | Impact (monetary) | Proximity | EV | Importance | Response(s) | Description
1 | Text recognication | Quality | Active | 2022-11-08 | 2022-11-09 | 2022-11-11 | Abdullah Rafique |  | Manahil Rana | Difficulty to recognise number of the car | Number plate not clear | Able to detect number plates | 75% to 100% | 15000 | This month | 0 |  | Optical character reader (OCR) can be used | OCR can be used to recongize text instead of using the basic camera
2 | Data security | Legal | Active | 2022-11-08 | 2022-11-09 | 2022-11-11 | Muskan Shah |  | Nischal | The login details and the data can be stolen from the database | Fear of being hacked | Data of the user can be secured | 50% to 75% | 20000 | Next 6 months | 150 | Medium | Encryption software such as Acronis Cyber or Atera can be used | Secure the app database from hacking by using security questions and two factor authenication
3 | Stealing vehicle information | Legal | Active | 2022-11-08 | 2022-11-09 | 2022-11-11 | Andrei |  | Manahil Rana | Mallicious users can spy or sell the vehicle details | Sensitive data about vehicles | Data of the vehicles can be secured | 50% to 75% | 15000 | Next 6 months | 0 | Medium | Deployment of the app on the right platform | This way each user can be verified and the data from the app will not be transferable to any other platform
4
5
6
- - - - PRINCE2® Templates - - - -
A guide for this template, it’s latest version, and all other templates are available at mplaza.pm/templates
Also, you may be interested in using our PRINCE2 eLearning Courses available at mplaza.pm
Copyright 2018, Management Plaza
You can use this document for free in your projects and for your personal purposes. Redistributing this document or using it for training requires permission from Management Plaza.
This document is based on AXELOS PRINCE2® material. Reproduced under licence from AXELOS. All rights reserved.

## Definitions
Type | Probability Label | Probability value for EV | Proximity | Status | Importance | Importance threshold
Schedule | 75% to 100% | 87% | This month | Active | High | 10000
Quality | 50% to 75% | 63% | Next 3 months | Closed | Medium | 5000
Legal | 25% to 50% | 38% | Next 6 months |  | Low | 0
Etc. | 10% to 25% | 18% | Far away
| 5% to 10% | 8%
| 0% to 5% | 2.5%